## To Do
TASK | Status
When creating new challenge, it is not available in my challenges list | Done
Create edit challenge api | Done
Amount sum is null on my challenges list | Done
File not showing in the submitted list after adding | Already Done
Finalize voting on challenge | Done
Result Calculation | Done
Get Paypal and fcm settings from database | Done
Add pagination in challenge submitted users list | Done
add review button key in challenge detail api
Add category filter in challenges get list api
add bid button key in challenge detail api
Send notification to user on vote on submitted challenge
Create edit challenge page for admin web
Add complete detail of challenge on challenge detail page for admin web
Short the text in value field when rendering settings table for admin web
on settings edit check the type of setting then show appropriate input type field for admin web
Remove payment gateways model table and navigation option for admin web

## Notifications
Event | Send To | Link
On Submit Challenge | Donator - Creator | CHALLENGE_DETAIL_SCREEN